## data
project_name_id | object | module | data_object_type | transformation_complexity | load_complexity | source_complexity | scope | object_development | iteration_1_data_loading | iteration_1_defects | iteration_2_data_loading | iteration_2_defects | iteration_3_data_loading | iteration_3_defects | production_data_loads | total
yash | Material | MM | Transactional data | Complex | 0-10000 | Medium | OutScope | [8 empty] | 0
yash | Material Inventory Balance | MM | Master Data | Medium | 0-10000 | Medium | OutScope | [8 empty] | 0
yash | Purchase Contract | MM | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Purchase order(Only Open PO) | MM | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Purchase scheduling agreement | MM | Transactional data | Medium | 0-10000 | Medium | InScope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Purchasing Info record | MM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Source List | MM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Business Partner - Customer | SD | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Business Partner - Supplier | SD | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Customer material info-record | SD | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Condition Record for Pricing in Purchasing | SD | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Sales order ( Only Open SO) | SD | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Sales Contract | SD | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Condition Record for Pricing in Sales | SD | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Condition Record for Pricing - General | SD | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | FI - Accounts Payable open items | FI/CO | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | FI - Accounts Receivable open items | FI/CO | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Activity Type | FI/CO | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | G/L balances- balance sheet accounts | FI/CO | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Profit Centre | FI/CO | Master data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | Cost Center | FI/CO | Master data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | FI - GL Account Balance and Open Line Item | FI/CO | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Exchange Rate | FI/CO | Master data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | Bank | FI/CO | Transactional data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | GL Account | FI/CO | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Fixed Asset | FI/CO | Transactional data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | Characteristics | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Class | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Batch Classification | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | QM - Inspection Plan | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | QM - Inspection Plan & Customer Specifications | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | QM - Inspection Method | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | QM - Master Inspection Characteristics | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Material Classification | QM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Work center | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | QM Info records Materials (QIR) | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | COA Profiles | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | CoA Assignment | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Inspection Method | QM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Material BOM | PP | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Recipe | PP | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Production Version | PP | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Routing | PP | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | PS - Project | PS | Transactional data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | PS - WBS Element | PS | Transactional data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Maintenance plan | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Equipment Classification | PM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Functional Location | PM | Master data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | Functional Location Classification | PM | Master data | Complex | 0-10000 | Medium | Inscope | 5 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 13
yash | Measuring Point | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Equipment | PM | Master data | Low | 0-10000 | Medium | Inscope | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6.5
yash | Equipment BOM | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Equipment task List | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Functional location BOM | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Functional location task list | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | General maintenance task list | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
yash | Maintenance Item | PM | Master data | Medium | 0-10000 | Medium | Inscope | 5 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 9.5
540.5